## Introduction
Welcome to the LOE Estimator
This template provides a Root Mean Square (RMS) estimate of the Level of Effort (LOE) for a project or project phase
A set of four spreadsheets are used to determine this LOE
If different stages of the project need to be estimated using team members in different roles, it is recommended to copy these spreadsheets within this workbook, determine the LOE from the copies, then add the LOEs and costs together for the total LOE and estimated costs
The four spreadsheets are as follows:
Epic Hours - the list of high level epics (or themes) that are expected to be completed, with these broken down into epics that have been sized
Epic Sizing - the range of hours used for each size in a "tee shirt" estimated range of hours to complete an epic
Estimated LOE - Cost - Duration - the team member roles, the estimated percentage of time spent in each role on the RMS hours determined from the epics, the relative amount of time spent by each role on UAT or integration testing for these epics and their rates are used to determine costs
For duration, the individual role with the most hours is used to estimate the work weeks for the project.
Pro Forma - the expected hours for each role across the duration of the project, as another way to validate the estimated timeline / hours / costs
The example entries in the Epic Hours and LOE and Cost spreadsheets are just that - examples. These should be replaced with the entries that are relevant for the project or project phase using this template
If it is necessary to modify content in protected spreadsheets, the default password is the name of our company

## Epic Sizing
EPIC sizing | Lower Limit (hours) | Upper Limit (hours) | Comment
S | 4 | 8
M | 8 | 16
ML | 16 | 32
M2L | 32 | 80 | Use when uncertain if medium or large
L | 80 | 120
XL | 120 | 160
XXL | 160 | 320
Custom | 0 | 0
Sub-Epics sum |  |  | Hours determined by the sub-Epics for this Epic (TBD)
Duplicate |  |  | Hours accounted for by a separate sub-Epic
Future |  |  | To (possibly) be implemented in a later project phase
If desired, you can change the Lower and Upper limits for a tee shirt size by entering your estimates directly
The Lower and Upper limits are in working hours, not the actual average hours worked per day
In selecting a tee shirt size for a sub-epic, include time estimated to be spent on all related work needed to complete its development (e.g., meetings, unit testing, defect resolution)
The epics and sub-epics in the Epic Hours spreadsheet are examples - you can add, modify, or delete these work items to match your project needs
Role | Billable Rate | RDC
Solution Architect | 250 | 150
Data Architect | 250 | 150
HX Strategist | 250 | 150
HX Researcher | 185 | 90
Creative | 185 | 90
Business Analyst | 185 | 90
QA Engineer | 185 | 90
SRE / Build Engineer | 185 | 90
Data Engineer | 185 | 90
Data Analyst | 185 | 90
Full Stack Dev | 185 | 90
UI / Front End Dev | 185 | 90
Project Manager | 185 | 90
Not Specified | 185 | 90 | Use a blended rate when the specific role is not specified
Unknown | 185 | 90 | Use a blended rate when the specific role is not specified

## Epic Hours
High-Level Theme or Feature | I want (an Epic) to | To support this Epic, a Sub-Epic/Story needs to be delivered to | Role | T-Shirt Size | Minimum Hours | Maximum Hours | Remarks
Kickoff
Crosscutting Role Activities
|  | Stakeholder Alignment | Project Manager | ML | 16 | 32
|  | Project Management | Project Manager | ML | 16 | 32
Initial Design Phase | [6 empty] | Expected to be a 30 day effort to start the project
HX Design
|  | Journey maps and other HX artifact development | Not Specified | M | 8 | 16
|  | Design Comps | Not Specified | M | 8 | 16
|  | Wireframes | Not Specified | M | 8 | 16
High Level System Architecture Design
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Business Domain Data Model Design
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Multi-tenant platform Foundation
Cloud Selection
|  | Evaluation | Not Specified | M | 8 | 16
|  | Contracting and Tenant Provisioning | Not Specified | M | 8 | 16
Data Platform Layer
|  | Analize current data model to identify suitability for multi-tenancy | Not Specified | XL | 120 | 160
|  | Evaluate available services for suitability | Not Specified | ML | 16 | 32
|  | Implement persistence store | Not Specified | XXL | 160 | 320
|  | Backup, monitoring and resiliency | Not Specified | XL | 120 | 160
Application Architecture
|  | Determine core use cases | Not Specified | M2L | 32 | 80
|  | Decompose into components | Not Specified | M2L | 32 | 80
|  | Document System Architecture | Not Specified | M2L | 32 | 80
|  | Team Alignment on Architecture | Not Specified | M2L | 32 | 80
Cloud Speciic Service Arch
|  | Evaluate services (bespoke vs. cloud-native) | Not Specified | M2L | 32 | 80
|  | Infrastructure and provisioning | Not Specified | XL | 120 | 160
Security and isolation
|  | Identity platform | Not Specified | M2L | 32 | 80
|  | Data Security and Isolation | Not Specified | ML | 16 | 32
|  | Network Security | Not Specified | M2L | 32 | 80
|  | Security Services (firewall, CDN and Edge) | Not Specified | L | 80 | 120
Design or select workflow engine
|  | Evaluation and Selection | Not Specified | M2L | 32 | 80
|  | Licensing and provisioning | Not Specified | ML | 16 | 32
Build Runtime environment
|  | Container orchestration | Not Specified | ML | 16 | 32
|  | Message bus/Event handling | Not Specified | M2L | 32 | 80
Provisioning and Build Pipelines
|  | Platform component provisioning code | Not Specified | XXL | 160 | 320
|  | Source code build pipeline and deployment | Not Specified | XL | 120 | 160
Monitoring and Alerting
|  | Service Evaluation and Selection | Not Specified | L | 80 | 120
|  | Provisioning | Not Specified | XL | 120 | 160
Lead & Feasibility
Auto-vet MLS/agent submissions
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
predict fit vs. criteria
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
highlight zoning/parcel constraints
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Natural-language queries for agents | [5 empty] | “What can I build on 123 Main?”) with instant feasibility summaries.
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Core workflow | [5 empty] | Implement existing business processes on the new platform
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Entitlement & Design
AI-assisted entitlement checks
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Correction-cycle prediction
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Permit packet generation
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Single status thread for builders/agents
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Consultant orchestration
|  | Auto Dispatch | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
|  | SLAs | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
|  | Handoffs | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
|  | Milestones | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Design accelerators | [5 empty] | Using the library of 1,500+ plan sets to produce rapid concepts that respect site constraints
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Core workflow | [5 empty] | Implement existing business processes on the new platform
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Builder Assignment & Development
| Recommendation engine for builder matching | [5 empty] | geo, history, quality, cost/variance, capacity
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Builder performance dashboards
|  | Pipeline Balance | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
|  | "Time-to-start" | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Core workflow | [5 empty] | Implement existing business processes on the new platform
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Lending & Servicing
Draws and progress tracking
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Early-risk signals | [5 empty] | inspection slippage, entitlement stalls
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Investor yield forecasting
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Core workflow | [5 empty] | Implement existing business processes on the new platform
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Data & Insights
Structured thread from intake through servicing
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Market trend lenses | [5 empty] | entitlement cycle times by jurisdiction; plan types that clear fastest
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
| Explore insight/API products | [5 empty] | post-Blueprint proof, with rights/controls
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Client Experience
| Conversational/voice agents | [5 empty] | answering “Where is my permit/draw right now?” and surfacing blockers.
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Move from PDF to interactive data exploration
|  | Queryable maps | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
|  | Entitlement/Utility Overlays | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
|  | Live Dashboards | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Core Workflows | [6 empty] | These are the core workflows that currently exist, that are not already included above.
Identify and document existing WF
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Documentation | Not Specified | M | 8 | 16
Core Workflow Implementation
|  | Implementation | Not Specified | M | 8 | 16
|  | Deployment | Not Specified | M | 8 | 16
Front End Development
Administrative UI
|  | Tenant onboarding | Not Specified | M | 8 | 16
|  | Tenant configuration | Not Specified | M | 8 | 16
Lead & Feasibility UI
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Entitlement & Design UI
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Builder Assignment & Development UI
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Lending and Serviceing UI
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Data and Insights UI
|  | Platform selection and implementation | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Project Close UI
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Implementation | Not Specified | M | 8 | 16
Back End Services
Database Implementation
|  | Schema | Not Specified | M | 8 | 16
|  | Stored Proceedures, Triggers | Not Specified | M | 8 | 16
Resource Access Components
|  | Code Development | Not Specified | M | 8 | 16
|  | Deployment | Not Specified | M | 8 | 16
Managers
|  | Code Development | Not Specified | M | 8 | 16
|  | Deployment | Not Specified | M | 8 | 16
Engines
|  | Code Development | Not Specified | M | 8 | 16
|  | Rules Development | Not Specified | M | 8 | 16
|  | Deployment | Not Specified | M | 8 | 16
Message bus/Eventing
|  | Code Development | Not Specified | M | 8 | 16
|  | Deployment | Not Specified | M | 8 | 16
API Development
|  | Code Development | Not Specified | M | 8 | 16
|  | Deployment | Not Specified | M | 8 | 16
Identity Management and security
|  | Code Development | Not Specified | M | 8 | 16
|  | Deployment | Not Specified | M | 8 | 16
Existing Connect - Global Tabs | [6 empty] | This theme involves functionality that is currently existing, Global tabs are primarily Lists and Search features
| Calendar | [5 empty] | Not covered in Demo
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
| Events | [5 empty] | Not covered in Demo
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Contacts
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Investors
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Projects
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Loans
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Admin
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Sales
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Existing Connect - Contacts | [6 empty] | This theme involves functionality that is currently existing, and will need to be rebuilt in the new Connect 2.0
| General Info | [5 empty] | Not covered in Demo
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
| Relationships | [5 empty] | Not covered in Demo
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Loans
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Credit
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Banking
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Lists
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Notes
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Existing Connect - Loans | [6 empty] | Some items have two rows of secondary tabs.
| Origination | [5 empty] | Two rows of secondary tabs. First secondary are states and activites
|  | Sub-tab: Borrowers | Not Specified | M | 8 | 16
|  | Sub-tab: Team | Not Specified | M | 8 | 16
|  | Sub-tab: Property | Not Specified | M | 8 | 16
|  | Sub-tab: Budget | Not Specified | M | 8 | 16
|  | Sub-tab: Terms | Not Specified | M | 8 | 16
|  | Sub-tab: Proforma | Not Specified | M | 8 | 16
|  | Sub-tab: Docs | Not Specified | M | 8 | 16
|  | Sub-tab: Web | Not Specified | M | 8 | 16
|  | Sub-tab: Audit | Not Specified | M | 8 | 16 | Includes validation logic
|  | Sub-tab: Notes | Not Specified | M | 8 | 16 | Some integration functionality
|  | Sub-tab: Funding | Not Specified | M | 8 | 16 | Includes validation logic
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Servicing
|  | Sub-tab: Loan Activity | Not Specified | M | 8 | 16
|  | Sub-tab: Statements | Not Specified | M | 8 | 16
|  | Sub-tab: Payoff Quotes | Not Specified | M | 8 | 16
|  | Sub-tab: Modifications | Not Specified | M | 8 | 16
|  | Sub-tab: Sales | Not Specified | M | 8 | 16
|  | Sub-tab: Assignment | Not Specified | M | 8 | 16
|  | Sub-tab: Reconveyances | Not Specified | M | 8 | 16
|  | Sub-tab: Draw History | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
| Draw Set | [5 empty] | Integration with iPad inspection app. Montly draw sets are created for every active project with funds still available.
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | iPad Integration | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Draw Funding
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Month End
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Borrowing Base
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Existing Connect - Projects
Info / Feasibility
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Proforma
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Permits
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Docs
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Agreements
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Invoices
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Team
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Notes
|  | Front End | Not Specified | M | 8 | 16
|  | Back End | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Existing BPO - Global Tabs | [6 empty] | This theme involves functionality that is currently existing
Home
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | Integrations | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
| Submit | [5 empty] | There are secondary tabs, but were not shown in the demo
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
Projects
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | Integrations | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Documents
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | Integrations | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
| Loans | [5 empty] | There are secondary tabs, but were not shown in the demo
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | Integrations | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
FAQ
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Home Search
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | GIS Integrations | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Settings
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Existing BPO - Projects | [6 empty] | This theme involves functionality that is currently existing
Workflow Integration (State Management)
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | Notifications | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
New Lead
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Lead Acquisition
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Messages
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Documents
|  | Front End | Not Specified | M | 8 | 16
|  | Back End | Not Specified | M | 8 | 16
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
| Duplicates | [5 empty] | Detects and flags duplicate documents
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Design SharePoint integration
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
Permit and Entitlement SharePoint integration
|  | Front End | Not Specified | ML | 16 | 32
|  | Back End | Not Specified | ML | 16 | 32
|  | UX/HX Design | Not Specified | M | 8 | 16
|  | Core Workflow | Not Specified | M | 8 | 16
|  | Totals (software development min/max hours) |  |  | 4680 | 9024
Theme 4
Epic 1
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic 2
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic 3
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Existing Connect - | [6 empty] | This theme involves functionality that is currently existing, and will need to be rebuilt in the new Connect 2.0
| Epic | [5 empty] | Not covered in Demo
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
| Epic | [5 empty] | Not covered in Demo
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Existing BPO - | [6 empty] | This theme involves functionality that is currently existing, and will need to be rebuilt in the new Connect 2.0
| Epic | [5 empty] | Not covered in Demo
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
| Epic | [5 empty] | Not covered in Demo
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16
Epic
|  | Sub-epic / Story | Not Specified | M | 8 | 16
|  | Sub-epic / Story | Not Specified | M | 8 | 16

## Role Hours
Role | Min Hours | Max Hours | RMS Role Hours | % Total Hours
| 0 | 0 | 0 | 0% | This should remain zero. It's an artifact of the UNIQUE formula
Project Manager | 32 | 64 | 51 | 0.7095%
Not Specified | 4648 | 8960 | 7137 | 99.29%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
Totals by Role | 4680 | 9024 | 7188 | 100%

## Estimated LOE - Cost - Duration
The (...Total min/max hours) shown below are computed from the Totals of min/max hours for software development in the "Epic Hours" spreadsheet
The RMS of Total min/max hours - SQRT ( (min*min + max*max)/2) - from the "Epic Hours" spreadsheet weights the maximum value more than does an average - (min + max)/2 - of these values
The Hours/Role are determined as the Allocation (%) for each role times the (RMS of Total min/max hours)
Cost is determined as the (Hours/Role + UAT&Integration Hours) * Rate for each Role
RMS of Total min/max dev hours = | 7188 | Modify values below as needed
|  | UAT & Integration Hours = |  | Hours/Role * | 5% | Percent of each role dedicated to UAT and Integration
|  | Expenses = |  | Total Work * | 0%
|  |  |  | Variance = | 10%
|  |  | Average % Actual Work/Week = |  | 100%
Role (an individual/line) | % of RMS Role hours | RMS Hours per Role | UAT & Integration Hours | Rate | Cost
Project Manager | 0.7095% | 51 | 3 | 185 | 9990
Not Specified | 99.29% | 7137 | 357 | 185 | 1386390
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
| 0% | 0 | 0 | 0 | 0
Left blank as a sum protector | 100%
Total Hours | 100% | 7188 | 360 | Total Work | 1396380
|  | Expenses (% of Total Work) |  |  | 0
|  | Total Estimated Cost |  |  | 1396380
|  | Low Variance |  |  | 1256742
|  | High Variance |  |  | 1536018
|  | Estimated Duration by role (40 hr weeks) |  |  | 187.5 | Review this value if PM is the long straw/critical path
|  | Low Variance |  |  | 169
|  | High Variance |  |  | 206.5

## Pro Forma
Role | Resource | Rate | LOE Hours | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Resource Hours | Sub-Total | Est. Hourly RDC | Est. Cost | Est. GM | Month | Milestone Payment Amount | With ECIF
Solution Architect |  | 225 | 51 | Week 1: 40; Week 2: 20 | 60 | 13500 | 140 | 8400 | 37.78% | February | 124915 | 99960
HX Strategist/Researcher |  | 225 | 7137 | Week 1: 40; Week 2: 20 | 60 | 13500 | 140 | 8400 | 37.78% | March | 124915 | 0
HX Researcher/Designer |  | 185 | 0 | Week 1: 40; Week 2: 20 | 60 | 11100 | 100 | 6000 | 45.95% | April | 124915 | 0
Full Stack Dev |  | 200 | 0 | Week 1: 15; Week 2: 15 | 30 | 6000 | 115 | 3450 | 42.5% | May | 124915 | 0
UI / Front End Dev |  | 185 | 0 | Week 1: 20; Week 2: 40 | 60 | 11100 | 110 | 6600 | 40.54%
Project Manager (focused on delivery) |  | 185 | 0 | Week 1: 15; Week 2: 15 | 30 | 5550 | 85 | 2550 | 54.05% | Professional Services Fees: | 499660 | 99960
Engagement/Delivery Manager |  | 225 | 0 | Week 1: 10; Week 2: 5 | 15 | 3375 | 140 | 2100 | 37.78%
|  |  | 7188 | [14 empty] | Revenue: | 64125 | Cost: | 37500 | 41.52%
| Total hourly rate | 1430 |  | Week 14: Avg Rate | 315 | 203.5714
| Number of roles | 8
| Avg. hourly rate | 178.75