# Detailed Workflow Group Analysis

VS4: Design & Entitlement

Blueprint Capital - Intelligent Operating Model v1.0

# 1. Purpose & Outcomes

Purpose:

Transform assigned properties from schematic design through permit-ready status by creating architectural plans, coordinating consultants, and securing municipal approvals for construction.

Key Outcomes:

- Approved permit sets ready for construction

- Design plans that meet builder requirements, budget constraints, site conditions, and local aesthetics

- Jurisdictional approval through correction cycle management

- Marketing and demo plan sets for builder use

Business Value:

Enables Blueprint to move properties from acquisition to construction while maintaining speed, quality, and builder satisfaction. Design Team capacity directly impacts throughput across entire operating model.

# 2. Entry & Exit Conditions

Entry Conditions:

- Project has received GO decision from VS2 (Feasibility)

- Property has been acquired or is in escrow (VS3)

- Builder has been assigned (VS3)

- Basic project information available: address, jurisdiction, builder assignment

- Timing requirements established by Acquisitions Team

- Ideal: 6-8 weeks advance notice before Design Team start; minimum: 4 weeks

Inputs from VS2 (Feasibility):

- Feasibility Assessment with site constraints, zoning analysis, tree coverage, neighboring property considerations

- Plan Set (Concept): Preliminary site plan options matched from library of ~1,500 existing plan sets

- Preliminary unit count and metrics for proforma

- Budget range estimates

Exit Conditions:

- Jurisdiction has issued approved permit (Permit Ready status)

- Approved permit set delivered to builder

- Marketing sets and demo plans delivered as needed

- All project documentation filed in SharePoint

Handoff to VS6 (Construction Servicing):

- Project status: Permit Ready

- Deliverables: Plan Set (Permit Approved), Plan Set (Demo), Plan Set (Marketing)

- Builder relationship transitioned to Construction Administration Team for ongoing support

- Note: Construction Administration (CA) Team operates within VS6 scope, providing on-site support, post-permit revisions, and feedback loops during active construction

# 3. Actors & Roles

## Design Team Structure

Managing Director - Design (1)

- Oversee Design Team schedule and coordination

- Provide critical information to Acquisitions Team for large-scale decisions

- Approve rollout of new Design Team processes

- Final approval for all Design Team hires

- Manage changes in Design Team structure (growth, scale-back)

- Provide stakeholders with team metrics (time, cost, production)

Senior Design Manager (3)

- Develop and finalize schematic floor and site plan designs with builder/customer

- Use current design trends, best practices, strong code knowledge

- Combine innovation with practical effectiveness for massing concepts

- Set expectations for construction administrative services (delivered in VS6)

- Provide customer feedback to strengthen Design Team processes

- Control final decisions for Design Team processes

- Participate in new hire process as needed

Design Manager (6)

- Manage production of construction documents and plan sets using redlines

- Ensure Design Associate understanding of zoning regulations and building codes

- Troubleshoot software issues for Design Associates

- Confirm drafting standards adhere to Design Team quality expectations

- Act as liaison and manage coordination with consultants, external customers, cross-functional teams

- Resolve problems by collecting and analyzing information from multiple sources

- Provide feedback for skill and leadership development to Design Associates

- Find areas of opportunity related to best practices for all Design Associate processes

- Assist onboarding and training for new Design Associates

- Present creative ideas to Senior Design Manager

- Provide Design Associate performance feedback (strengths and opportunities) to Managing Director

Senior Design Associate (2)

- Produce construction documents and plan sets on high complexity projects

- Acquire approved permit set within expedited correction process timing (1-2 rounds)

- Incorporate feedback within one round of iterations (redlines) from Design Manager

- Understand complex zoning regulations and building codes

- Brainstorm and problem solve by self-recognizing potential issues with minimal assistance

- Coordinate and communicate with Design Team management, consultants, cross-functional teams with minimal assistance

- Utilize all Design Team software with ability to complete complex tasks and troubleshoot issues without assistance

- Understand high-quality drafting standards to adhere to Design Team quality expectations

- Use time management skills and multitasking abilities to prioritize tasks and complete deadlines with little to no assistance

- Take on special design tasks with proficiency

- Provide peer support to other Design Associates

- Exemplify strong leadership values of the Design Team

- Provide valuable feedback on best practices

Design Associate (8)

- Produce construction documents and plan sets on complex projects

- Acquire approved permit set within quick correction process timing (2 rounds)

- Incorporate feedback within approximately 2 rounds of iterations (redlines) from Design Manager

- Understand in-depth zoning regulations and building codes

- Brainstorm and problem solve by self-recognizing potential issues with assistance from Design Manager

- Coordinate and communicate with Design Team management, consultants, cross-functional teams with assistance

- Utilize all Design Team software with ability to complete tasks and troubleshoot issues without assistance

- Understand quality drafting standards to adhere to Design Team quality expectations

- Use time management skills and multitasking abilities to prioritize tasks and complete deadlines with minimal assistance

Junior Design Associate (4)

- Produce construction documents and plan sets on re-use designs and minimal complexity projects

- Acquire approved permit set within average correction process timing (2-3 rounds)

- Incorporate feedback within approximately 2-3 rounds of iterations (redlines) from Design Manager

- Understand simple zoning regulations and building codes

- Brainstorm and problem solve with given callouts from Design Manager

- Coordinate and communicate with Design Team management, consultants, cross-functional teams with assistance from Design Manager

- Utilize all Design Team software with ability to complete tasks and troubleshoot issues with assistance

- Understand simple drafting standards to adhere to Design Team quality expectations

- Use time management skills and multitasking abilities to prioritize tasks and complete deadlines with assistance from Design Manager

Process Improvement (PI) Team

- Ensure continuous improvement and efficiency within Design Team

- Manage all standard procedures including new jurisdictions

- Directly support Design Managers with processes involved in design development and construction documents

- Provide decision-making information to Design Management Team

- Support business as a whole with Design Team growth areas

## Entitlement Team Structure

Entitlements Manager (1)

- Oversee entitlement intake and tracking

- Manage Entitlement Associates

- Ensure permit-ready status achieved

- Coordinate with jurisdictions

Entitlement Associates (2)

- Submit permit packets to jurisdictions (Seattle, Kirkland, Bellevue WA, Phoenix area AZ)

- Track correction cycles and resubmittals

- Coordinate with consultants for required documents

- Manage jurisdiction-specific requirements

- Update tracking in SharePoint continuously

Feasibility Coordinator (1)

- Support feasibility phase design work (within VS2 scope)

- Coordinate initial project information handoff from Acquisitions to Design

- Interface between Acquisitions and Design Teams

Managing Director - Land Use Policy (1)

- Advisory role on jurisdiction requirements

- Policy and regulatory guidance

- Strategic zoning and land use counsel

## External Stakeholders

Builders (Customers)

- Receive design plans and provide input during schematic design phase

- Primary customer for approved permits, marketing sets, demo plans

Consultants

- Survey: Property boundaries and topography

- Civil Engineer: Site grading, drainage, utilities

- Structural Engineer: Structural design elements

- Landscape: Site landscaping plans

- Arborist: Tree removal and retention when significant trees present

Jurisdictional Plan Reviewers

- Seattle, Kirkland, Bellevue (Washington): Established procedures and relationships

- Phoenix area (Arizona): Expanding market; may require more attorney involvement

Acquisitions Team

- Provides inputs (project info, budget constraints, timing requirements)

- Receives outputs (schedule information, approved permits, marketing support)

# 4. Workflow Groups

Value Stream 4 operates across four Workflow Groups spanning from schematic design through permit approval:

Workflow Group & Workflow Numbering System

VS4 uses a hierarchical three-level numbering system:

Level 1: Value Stream (VS) - ex: VS4 = Design & Entitlement

Level 2: Workflow Group (WG) - Major workflow phases that group related activities - Format: VS4-WG# or shorthand 4.#

Level 3: Workflow (WF) - Individual workflows within a Workflow Group - Format: VS4-WG#-WF# or shorthand 4.#.#

VS4 Workflow Group Examples:

- WG1 (4.1): Schematic Design - 3 Workflows

- WG2 (4.2): Design Development - 6 Workflows

- WG3 (4.3): Entitlement Execution - 7 Workflows

- WG4 (4.4): Supporting Deliverables - 2 Workflows

Total: 18 Workflows across 4 Workflow Groups

Usage Examples: - Full notation: VS4-WG1-WF1 (technical documentation) - Shorthand: 4.1.1 (diagrams, tracking systems) - Human-readable: “VS4 > Schematic Design > Initiation” (presentations)

## Workflow Group 1: Schematic Design (Post-GO, Pre-Permit)

### Workflow 4.1.1 - Schematic Design Initiation

#### VS4-WG1-WF1

Actor: Senior Design Manager

Trigger: GO decision from VS2, property acquired/in escrow from VS3, builder assigned

Input Objects: Project, Property (Owned), Builder (Assignment), Feasibility Assessment, Plan Set (Concept)

Activities:

- Receive project information from Acquisitions Team: address, jurisdiction, timing callouts from standards, builder information

- Receive local zoning updates and intake date from Entitlement Team

- Receive Feasibility Assessment and conceptual plan set from VS2

- Confirm all constraining project information has been provided

- Ideal timeline: Project info received 6-8 weeks before start; minimum 4 weeks

Output Objects: Project Assignment

Constraint: Design Team will not start project within 4 weeks of receipt to mitigate variable input risks

Typical Duration: Setup window

### Workflow 4.1.2: Schematic Floor & Site Plan Development

#### VS4-WG1-WF2

Actor: Senior Design Manager (with Design Manager support)

Input Objects: Project, Property, Builder requirements, Feasibility Assessment, Zoning, Code requirements

Activities:

- Develop schematic floor plans for each unit

- Create detailed site plan with design requirements

- Consider builder-specific needs and preferences

- Consider Acquisitions Team budgeting and marketing requirements

- Incorporate existing and potential site conditions

- Consider architectural style of neighboring properties

- Consider overall aesthetic of local vicinity and territorial views

- Use current design trends and best practices

- Apply strong knowledge of all codes

- Combine innovation with practical effectiveness for massing concepts

Output Objects: Plan Set (Schematic) with floor plans, site plan, preliminary massing

Decision Point: Builder/Acquisitions approval of schematic design (D4.1)

Typical Duration: Part of overall 2-3 week project cycle (productivity-dependent)

### Workflow 4.1.3: Rendered Images Creation

#### VS4-WG1-WF3

Actor: Design Associate

Tools: Lumion, SketchUp

Input Objects: Plan Set (Schematic)

Activities:

- Create 3D rendered images of proposed design

- Show design in context of site and neighboring properties

Output Objects: Rendered Images

Handoff: To Acquisitions and builder for review

Typical Duration: Part of schematic design phase

## Workflow Group 2: Design Development & Permit-Ready Plans

### Workflow 4.2.1: Design Development Initiation

#### VS4-WG2-WF1

Actor: Design Manager assigns to Design Associate(s) based on complexity

Input Objects: Project, Plan Set (Schematic), Builder feedback

Activities:

- Assign project to appropriate Design Associate level based on complexity:

- • Junior Design Associate: Re-use designs, minimal complexity

- • Design Associate: Complex designs

- • Senior Design Associate: High complexity designs

- Set expectations for quality and timeline

Output Objects: Project Assignment

Decision Point: Design Associate Assignment (D4.2)

Typical Duration: At project kickoff

### Workflow 4.2.2: Construction Document Production

#### VS4-WG2-WF2

Actor: Design Associate (with Design Manager oversight)

Input Objects: Project, Plan Set (Schematic), Code requirements, Zoning, Builder requirements

Activities:

- Produce detailed construction documents and plan sets

- Follow Design Team guidelines, templates, reference material from Design Team Handbook

- Organize digital files per Design Team guidelines

- Adhere to drafting standards for Design Team quality expectations

- Understand and apply zoning regulations and building codes

- Use Design Team software: Revit (primary), AutoCAD, Bluebeam, SketchUp, Microsoft 360

- Coordinate with consultants as needed (routed through Design Manager)

- Support business brand standards with team-player attitude

Output Objects: Plan Set (Development) - construction documents in progress

Quality Check: Design Manager redlines

Typical Duration: Part of 2-3 week project cycle, varies by associate level and complexity

Iteration: 1-3 rounds of redlines depending on Design Associate level:

- • Junior Design Associate: 2-3 redline iterations expected

- • Design Associate: 2 redline iterations expected

- • Senior Design Associate: 1 redline iteration expected

Decision Point: Design Quality Gates - each redline iteration (D4.3)

### Workflow 4.2.3: Consultant Coordination

#### VS4-WG2-WF3

Actor: Design Manager (liaison), Entitlement Coordinator (orders)

Input Objects: Plan Set (Development), Project, Property, Consultant requirements

Activities:

- Design Manager acts as liaison; coordinates with:

- • Landscape consultant

- • Civil engineer

- • Structural engineer

- • Other consultants as needed

- Entitlement Coordinator places consultant orders

- Ensure consultant deliverables integrate with plan sets

- Track consultant status and deliverables manually

Output Objects: Consultant Documents (landscape plans, civil, structural), updated Plan Set (Development)

Pain Point: Consultant return times can cause production delays; work is critical and typically cannot be skipped or reordered

Constraint: Expectations set with consultants, but more coordination needed to ensure they can cover business needs

Typical Duration: Concurrent with design development, subject to consultant SLAs (no formal SLAs established)

### Workflow 4.2.4: Entitlement Team Coordination

#### VS4-WG2-WF4

Actor: Design Manager, Entitlement Coordinator

Input Objects: Plan Set (Development), Zoning, Code requirements

Activities:

- High level of coordination for permitting dates

- In-depth analysis of zoning and codes items:

- • Tree removal and retention requirements

- • Easement implications

- • Other jurisdiction-specific requirements

- Receive local zoning updates from Entitlement Team

- Continuous updating in SharePoint Project Tracker

Output Objects: Entitlement requirements documentation, updated Plan Set

System: SharePoint Project Tracker (continuous updating)

Typical Duration: Throughout design development phase

### Workflow 4.2.5: Additional Exhibits for Permitting

#### VS4-WG2-WF5

Actor: Design Associate

Input Objects: Plan Set (Development), Acquisitions requirements

Activities:

- Create JUMA exhibits (if required by jurisdiction)

- Create side sewer exhibits (if required)

- Produce any other jurisdiction-specific exhibits

Output Objects: Additional permit exhibits

Triggered by: Acquisitions Team requests based on jurisdiction requirements

Typical Duration: Part of design development

### Workflow 4.2.6: Permit-Ready Plan Set Finalization

#### VS4-WG2-WF6

Actor: Design Manager (final review), Design Associate (execution)

Input Objects: Plan Set (Development), all consultant documents, all exhibits

Activities:

- Incorporate all consultant work

- Incorporate all required exhibits

- Perform final quality control review

- Ensure all jurisdiction requirements met

- Confirm drafting standards and completeness per Design Team quality expectations

Output Objects: Plan Set (Permit) - complete, permit-ready

Decision Point: Is plan set complete and ready for jurisdiction submission? (D4.4)

Handoff: To Entitlement Team for submission

Typical Duration: Final stage of 2-3 week design cycle

## Workflow Group 3: Permit Submission & Correction Cycles

### Workflow 4.3.1: Entitlement Intake

#### VS4-WG3-WF1

Actor: Entitlements Manager

Input Objects: Project, Plan Set (Permit), all supporting documents

Activities:

- Receive permit-ready plan set from Design Team

- Confirm completeness of permit packet materials

- Log project in SharePoint permit tracker

Output Objects: Entitlement (Open status)

System: SharePoint (multiple sites: due diligence + permit tracking)

Pain Point: Work split across multiple SharePoint sites; no single view of status

Typical Duration: Intake checkpoint

### Workflow 4.3.2: Permit Packet Assembly

#### VS4-WG3-WF2

Actor: Entitlement Associate, Design Manager (support)

Input Objects: Plan Set (Permit), Consultant Documents, Supporting Documents

Activities:

- Assemble complete permit packet per jurisdiction requirements

- Include all required forms and supporting documentation

- Confirm all consultant documents included

- Manual compilation process

Output Objects: Permit Packet (complete)

Pain Point: Manual assembly process; city-specific requirements not codified in system

Typical Duration: Variable by jurisdiction complexity

### Workflow 4.3.3: City Submission

#### VS4-WG3-WF3

Actor: Entitlement Coordinator

Input Objects: Permit Packet

Activities:

- Submit permit packet to jurisdiction (Seattle, Kirkland, Bellevue WA, Phoenix area AZ)

- Log submission date and expected review timeline

- Track submission in SharePoint

Output Objects: City Submission

System: SharePoint + jurisdiction portal

Typical Duration: Submission event

SLA Note: No formal SLA with jurisdictions; timelines vary significantly by jurisdiction

### Workflow 4.3.4: Jurisdiction Review (Wait State)

#### VS4-WG3-WF4

Actor: Jurisdictional Plan Reviewer (external)

Activities:

- Jurisdiction reviews submitted permit packet

- Identifies code compliance issues

- Generates correction list

Duration: Variable by jurisdiction; no Blueprint control

Pain Point: No visibility into jurisdiction status; passive wait state; no proactive alerts

### Workflow 4.3.5: Correction Cycle Handling

#### VS4-WG3-WF5

Actor: Entitlement Associate (coordinator), Design Associate (execution), Consultants (as needed)

Input Objects: Correction Cycle (city comments), Plan Set (Permit), Consultant Documents

Activities:

- Receive correction list from jurisdiction

- Route corrections to appropriate Design Associate or consultant (Decision Point D4.5)

- Design Associate updates plan set to address corrections

- Consultants update their documents as needed

- Respond within jurisdiction-specified timeframe

- Track correction status in SharePoint manually

Output Objects: Plan Set (Permit) - revised, Correction Cycle (addressed)

Iteration: Multiple correction cycles are standard (typically 1-3 rounds):

- • Junior Design Associate projects: Average 2-3 correction rounds

- • Design Associate projects: Average 2 correction rounds

- • Senior Design Associate projects: Average 1-2 correction rounds

Pain Point: Manual tracking of correction cycles; dependencies with Design Team not visible in one system; no integration between SharePoint and other systems

Typical Duration: Variable by complexity; correction response must meet jurisdiction deadlines

### Workflow 4.3.6: Resubmittal & Tracking

#### VS4-WG3-WF6

Actor: Entitlement Associate

Input Objects: Plan Set (Permit) - revised, Correction Cycle responses

Activities:

- Resubmit revised plan set to jurisdiction

- Log resubmittal date

- Track resubmittal deadlines manually

Output Objects: City Submission (resubmittal)

Decision Point: Have all corrections been adequately addressed for resubmittal? (D4.6)

Pain Point: Manual tracking; filing and organizing city correspondence; tracking resubmission deadlines as administrative task

Iteration: Repeat cycle until approved (typically 1-3 cycles)

Typical Duration: Per jurisdiction requirements

### Workflow 4.3.7: Permit Ready Status Achieved

#### VS4-WG3-WF7

Actor: Entitlements Manager

Input Objects: City Submission (approved), Entitlement

Activities:

- Receive jurisdiction approval

- Update project status to Permit Ready

- Notify Design Team, Acquisitions, builder

- File approved permit set in SharePoint

Output Objects: Entitlement (Approved status), Plan Set (Permit Approved)

Handoff: To VS6 (Construction Servicing) and Construction Administration Team

Typical Duration: Approval event

Exit Condition: Project can now proceed to construction

## Workflow Group 4: Supporting Deliverables (Parallel Activities)

### Workflow 4.4.1: Marketing Set Development

#### VS4-WG4-WF1

Actor: Design Associate

Input Objects: Plan Set (Schematic or Development), Project, Builder requirements

Activities:

- Develop marketing sets for Acquisitions Team and builder use

- Include key floor plans, renderings, site plan

- Format for marketing materials

Output Objects: Plan Set (Marketing)

Output Recipient: Acquisitions Team, Builder

Timing: Developed during or after schematic design phase

Purpose: Support builder sales and marketing efforts

### Workflow 4.4.2: Demo Plan Set Creation

#### VS4-WG4-WF2

Actor: Design Associate

Input Objects: Plan Set (Permit Approved or near-final), Property

Activities:

- Create demo plan set showing demolition of existing structure

- Required to begin construction process

Output Objects: Plan Set (Demo)

Output Recipient: Builder

Timing: Often needed before permit fully approved to begin site prep

Typical Duration: Part of overall design cycle

# 5. Decision Points

D4.1: Schematic Design Approval

- Workflow: 4.1.2 - Schematic Floor & Site Plan Development

- Owner: Senior Design Manager → Builder + Acquisitions

- Question: Does schematic design meet builder requirements, budget, and site conditions?

- Data Inputs: Schematic plans, builder feedback, proforma constraints, code compliance check

- Approval Authority: Builder (customer approval), Acquisitions Team (budget approval)

- Escalation: Managing Director - Design, Managing Director - Acquisitions

- Outcome: Proceed to design development OR iterate schematic

D4.2: Design Associate Assignment

- Workflow:4.2.1 - Design Development Initiation

- Owner: Design Manager

- Question: Which Design Associate level is appropriate for project complexity?

- Data Inputs: Project complexity (re-use, minimal, complex, high complexity), associate availability, associate skill level

- Decision Logic:

- • Re-use designs, minimal complexity → Junior Design Associate

- • Complex designs → Design Associate

- • High complexity designs → Senior Design Associate

- Approval Authority: Design Manager

- Outcome: Project assigned to appropriate associate

D4.3: Design Quality Gates (Redlines)

- Workflow: 4.2.2 - Construction Document Production (iterative)

- Owner: Design Manager

- Question: Does design meet quality standards and can proceed to next iteration?

- Data Inputs: Draft plan set, Design Team standards, code compliance, builder requirements

- Approval Authority: Design Manager

- Decision Criteria:

- • Junior Design Associate: 2-3 redline iterations expected

- • Design Associate: 2 redline iterations expected

- • Senior Design Associate: 1 redline iteration expected

- Outcome: Proceed to next iteration OR approved for next stage

D4.4: Permit-Ready Completeness Check

- Workflow: 4.2.6 - Permit-Ready Plan Set Finalization

- Owner: Design Manager (execution), Entitlements Manager (acceptance)

- Question: Is plan set complete and ready for jurisdiction submission?

- Data Inputs: Plan set, consultant documents, jurisdiction requirements checklist, quality standards

- Approval Authority: Design Manager (execution), Entitlements Manager (acceptance)

- Escalation: Managing Director - Design

- Outcome: Release to Entitlement Team OR return for corrections

D4.5: Correction Routing & Assignment

- Workflow: 4.3.5 - Correction Cycle Handling

- Owner: Entitlement Associate

- Question: Who should address each correction item (Design Associate vs. Consultant)?

- Data Inputs: Correction list from jurisdiction, scope of corrections

- Decision Logic:

- • Plan set corrections → Route to appropriate Design Associate (by original assignment)

- • Consultant document corrections → Route to specific consultant (civil, structural, landscape, arborist)

- • Ambiguous corrections → Coordinate between Design Manager and consultant

- Approval Authority: Entitlement Associate (routing), Design Manager (validation)

- Outcome: Corrections assigned and tracked

D4.6: Resubmittal Readiness

- Workflow: 4.3.6 - Resubmittal & Tracking

- Owner: Entitlement Associate

- Question: Have all corrections been adequately addressed for resubmittal?

- Data Inputs: Revised plan set, correction list, consultant updates

- Approval Authority: Entitlement Associate (completeness), Entitlements Manager (final check)

- Outcome: Resubmit to jurisdiction OR return for additional corrections

# 6. Data & Canonical Objects

Primary Objects:

- Project: Central record linking all design and entitlement activities; tracks status through Workflows

- Property (Owned): Physical property being developed; includes address, jurisdiction, parcel data, site conditions

- Plan Set: Core deliverable evolving through lifecycle

- • Plan Set (Concept): Feasibility-phase conceptual plans [from VS2]

- • Plan Set (Schematic): Schematic design with floor plans, site plan, renderings

- • Plan Set (Development): Design development construction documents in progress

- • Plan Set (Permit): Final permit-ready construction documents

- • Plan Set (Marketing): Marketing-focused plan subset

- • Plan Set (Demo): Demolition plans

- Entitlement: Tracking record for permit submission and approval process; links to jurisdiction

- Permit Packet: Complete submission package to jurisdiction; includes Plan Set (Permit) and all supporting documents

- Correction Cycle: Record of jurisdiction feedback and correction responses; iterative

Secondary Objects:

- Builder (Assignment): Customer receiving design services and approved permits

- Consultant Order: Request and tracking for external consultant work

- Consultant Documents: Deliverables from external consultants integrated into plan sets

- City Submission: Record of submission events to jurisdiction; tracks dates and status

- Rendered Images: 3D visualizations of proposed design (created using Lumion, SketchUp)

- Document: General supporting documents (zoning, codes, site analysis, correspondence)

- Task: Work assignments and tracking within Design Team

- Redline: Design Manager feedback annotations requiring Design Associate corrections

- Design Team Assignment: Internal tracking of which Design Associate owns which project

- Feasibility Assessment: Output from VS2 providing constraints and initial analysis [input from VS2]

- Jurisdiction: Seattle, Kirkland, Bellevue (WA), Phoenix area (AZ); each with unique requirements

- Zoning: Applicable zoning regulations for property

- Code Requirements: Building codes and standards applicable to jurisdiction and project type

Data Flows:

FROM Acquisitions Team (VS2):

- Project information (address, jurisdiction, timing callouts from standards)

- Builder information

- Feasibility Assessment

- Budget constraints and marketing requirements

FROM Entitlement Team (internal coordination):

- Local zoning updates

- Intake date

- Tracking updates (SharePoint continuous)

- Consultant information

TO Acquisitions Team:

- Schedule information (to determine intake dates and project timing)

- Approved permits

- Marketing sets

TO Entitlement Team (internal handoff):

- Permit-ready plan sets

TO Builders (external customers):

- Approved permit sets

- Marketing sets

- Demo plans

TO Leadership Team:

- Design Team metrics (schedule, quality, scope, resource utilization)

TO VS6 (Construction Servicing):

- Approved permits

- Construction-ready status

- Plan Set (Permit Approved), Plan Set (Demo), Plan Set (Marketing)

Systems & Tools:

- SharePoint: Primary system for project tracking, document storage; multiple sites (due diligence + permit tracking) cause fragmentation

- Revit: Primary design and construction document production software

- AutoCAD: Additional design and drafting software

- Bluebeam: PDF markup and coordination

- SketchUp: 3D modeling

- Lumion: Rendering software for visualization

- Microsoft 360: Excel (tracking), Word (documentation), Outlook (communication), Teams (collaboration)

- Design Team Intranet: Templates, standards, reference materials, Design Team Handbook

- Online Code Databases: Jurisdiction-specific code references for all jurisdictions

- GIS Systems: Geographical Information Services for all jurisdictions

- Parcel Information Systems: Property data for all jurisdictions

# 7. Constraints & Rules

Timing Constraints (Impact Workflow):

- Project Start Rule: Design Team will not start project within 4 weeks of receipt; ideal is 6-8 weeks advance notice

- Rationale: Mitigate variable input risks; ensure Acquisitions Team provides all constraining project information needed to start

- Coordination Requirement: Proactive coordination with Acquisitions Team required to minimize risks of input variables

- Cadence Check-ins: Cadence of check-ins with Acquisitions Team to ensure projections steady

- Consultant Return Time: Consultant work is critical piece in multiple workflows; typically cannot be skipped or moved; delays cause production constraints across Design Team

- Consultant Coordination: Expectations set with consultants but more coordination needed to ensure consultants can cover business needs

- Jurisdiction Review Timelines: Variable by jurisdiction; no formal SLAs; correction response deadlines must be met

Quality Standards (Impact Workflows):

- Correction Cycle Expectations:

- • Junior Design Associate: 2-3 correction rounds to achieve approved permit

- • Design Associate: 2 correction rounds

- • Senior Design Associate: 1-2 correction rounds

- Redline Iteration Expectations:

- • Junior Design Associate: 2-3 iterations

- • Design Associate: 2 iterations

- • Senior Design Associate: 1 iteration

- Drafting Standards: Design Team quality expectations must be met per guidelines, templates, reference materials from Design Team Handbook

- Code Compliance: All designs must meet zoning regulations and building codes for applicable jurisdiction

Coordination Rules (Impact Workflow Execution):

- High Coordination with Entitlement Team Required for:

- • Permitting dates

- • Zoning and codes analysis

- • Tree removal and retention requirements

- • Easement implications

- Consultant Coordination Pattern: Design Manager acts as liaison; Entitlement Coordinator places consultant orders

- Cross-Functional Input Requirements:

- • Builder requirements and preferences (schematic design phase)

- • Acquisitions Team budget and marketing requirements (schematic design phase)

- • Existing and potential site conditions (all phases)

- • Neighboring property aesthetics and local vicinity considerations (schematic design phase)

Variable Input Rules (Impact Workflow Stability):

- Volume Dependency: Design Team can only meet projected number of completed projects if number of projects received from Acquisitions Team is met

- Cadence Dependency: Rate of project receipt needs to be relatively consistent; ebb and flow of incoming projects cannot be compromised in Design Team workflow cycle

- Mitigation: Cadence of check-ins with Acquisitions Team to ensure projections are steady

- External Work: Taking work from sources outside company vetted as solution to backfill downtime; results established negative ROI; can be considered case-by-case basis

Process Standardization (Impact System Requirements):

- All Standard Procedures: Managed by Process Improvement (PI) Team

- New Jurisdictions: PI Team establishes standardized workflows and templates; requires setup time that impacts throughput

- Tools and Resources: Created for new jurisdictions, to stay current with code changes, to match business growth/reduction projections

Note: Capacity constraints including staffing forecasts and productivity calculations have been moved to Appendix A.

# 8. Variations & Exceptions

Project Complexity Variations:

Re-Use Designs (Minimal Complexity):

- Assigned to Junior Design Associate

- Use existing plan sets from library of ~1,500 plans

- Adapt to site-specific conditions

- Faster cycle time

Complex Designs:

- Assigned to Design Associate

- Require more significant design work

- May require more consultant coordination

- Standard cycle time

High Complexity Designs:

- Assigned to Senior Design Associate

- Unique site challenges or design requirements

- Heavy consultant coordination

- May require Senior Design Manager direct involvement

- Potentially longer cycle time

Jurisdiction Variations:

Seattle, Kirkland, Bellevue (Washington):

- Established procedures and relationships

- Design Team has deep experience

Phoenix Area (Arizona):

- Expanding market

- May require more attorney involvement

- Different code requirements

- Building expertise

Each Jurisdiction Has Unique:

- Zoning regulations and building codes

- Permit submission processes and forms

- Review timelines and SLAs (or lack thereof)

- Correction cycle patterns

- Required exhibits and supporting documents

Consultant Variations:

- Survey: Required for most projects; addresses property boundaries and topography

- Civil Engineer: Required for site grading, drainage, utilities

- Structural Engineer: Required for structural design elements

- Landscape: Required for site landscaping plans

- Arborist: Required when significant trees present; addresses tree removal/retention

- Additional Consultants: May be needed based on site-specific conditions

Special Deliverable Requests:

- JUMA Exhibits: Required by some jurisdictions; created by Design Associate upon Acquisitions Team request

- Side Sewer Exhibits: Required for sewer connection plans; created upon request

- Additional Marketing Materials: May be requested by builder or Acquisitions beyond standard marketing sets

- Early Demo Plans: May be requested before full permit approval to enable site preparation

Timing Exceptions:

- Rush Projects: Occasionally projects may need expedited timelines; requires Design Manager approval and may disrupt standard workflow

- Delayed Projects: Projects may be paused due to builder financing, market conditions, or other external factors

- Phased Projects: Large projects may be designed and permitted in phases

Resource Allocation Exceptions:

- Special Design Tasks: May be assigned to Senior Design Associates with specific expertise

- Training Projects: New Design Associates may work on practice projects (1 month training period) before live assignments

- Peer Support: Senior Design Associates may provide support to other associates on complex issues

# 9. Pain Points & Failure Modes (Current State)

System Fragmentation:

- Work split across multiple SharePoint sites and trackers (due diligence site + permit tracker)

- No single view of status across jurisdictions and projects

- No integration between SharePoint and BPO or Connect

- Manual tracking of correction cycles and resubmittals

- Document compilation for permit packets is manual process

- Filing and organizing city correspondence is manual

Visibility & Coordination:

- Dependencies with Design Team not visible in one system

- Consultant status and deliverables tracked manually

- No structured view of consultant return times or SLAs

- City-specific requirements and timelines not codified

- Tracking resubmission deadlines is manual administrative task

- No proactive alerts for upcoming deadlines or delays

Variable Inputs (External Dependencies):

Acquisitions Project Volume & Cadence:

- Design Team can only meet projected number of completed projects if Acquisitions Team provides consistent volume

- Ebb and flow of incoming projects can disrupt Design Team workflow cycle

- Outside work vetted as backfill solution but established negative ROI

- Requires cadence of check-ins with Acquisitions Team to ensure projections steady

Consultant Return Times:

- Critical piece in multiple workflows; typically cannot be skipped or moved in process

- Delays cause production constraints across Design Team

- Expectations set with consultants but more coordination needed to cover business needs

Capacity & Resource Allocation:

- Design Managers have limited time to allocate to each Design Associate

- Design Team capacity limited to maximum number of Design Associates per forecast (see Appendix A)

- Ongoing growth will require additional staffing resources

- Work requires optimization to reduce Design Manager time per associate

Quality & Iteration:

- Correction cycle expectations (1-3 rounds) still require significant Design Associate time

- Junior Design Associates require 2-3 correction rounds; impacts project throughput

- Redline iterations (1-3 rounds per project) consume Design Manager time

- No structured feedback loop from correction patterns to process improvement

Knowledge & Training:

- New hire onboarding is 1 month; represents capacity drain during training

- New jurisdictions require PI Team to establish procedures; setup time impacts throughput

- Design Team reference materials and handbook require maintenance to stay current

- Skill development and advancement paths for Design Associates not fully systematized

# 10. Metrics & Signals

Volume & Throughput Metrics:

- Projects Completed Per Year: Target 140 (2025), 160 (2026), 180 (2027) [see Appendix A for capacity analysis]

- Current Output: 122-184 projects/year depending on productivity level [see Appendix A]

- Work Weeks Per Year Per Design Associate: 46 weeks (52 weeks - 3 weeks holidays - 3 weeks PTO)

- Average Project Cycle Time:

- • High Productivity: 2 weeks per project

- • Medium Productivity: 2.5 weeks per project

- • Low Productivity: 3 weeks per project

- Design Associate Utilization: Percentage of available weeks allocated to active projects

- Resource Capacity: Availability and allocation of Design Associates

- Resource Utilization: How effectively Design Associates are being used; identify bottlenecks or underutilization

Schedule Performance Metrics:

- Schedule Variance (SV): Actual progress vs. planned progress (ahead or behind schedule)

- On-Time Completion Rate: Percentage of tasks/projects completed within planned timeframe

- Project Cycle Time: Time from Design Team start to Permit Ready status

- Planned vs. Actual Work Hours: Comparison of planned hours vs. actual hours spent

- Time to Permit Ready: Duration from project assignment to approved permit issuance

Quality Performance Metrics:

- Correction Cycles Per Project:

- • Target: Junior ≤3 rounds, Associate ≤2 rounds, Senior ≤2 rounds

- • Actual: Track by associate and project complexity

- Number of Corrections Per Cycle: Total correction items from jurisdiction per review cycle

- Redline Iterations Per Project:

- • Target: Junior ≤3 iterations, Associate ≤2 iterations, Senior ≤1 iteration

- • Actual: Track by associate and phase

- Number of Deviations from Standard Processes: Exceptions requiring manual intervention or rework

- Defect Rate: Number of defects or errors found in project deliverables

Coordination & Handoff Metrics:

- Information Receipt Timing: Percentage of projects receiving all required information within 6-8 week ideal window vs. 4-week minimum

- Consultant Delivery Time: Time from consultant order to deliverable receipt

- Consultant Deliverable Quality: Rate of consultant deliverables requiring revision

- Entitlement Handoff Quality: Percentage of permit-ready plan sets accepted by Entitlement Team without returns

Leading Indicators (Early Warning Signals):

- Acquisitions Project Intake Rate: Weekly/monthly volume of new projects entering Design Team pipeline

- Cadence Consistency: Variability in project intake rate (consistent vs. ebb and flow)

- Design Associate Workload Balance: Distribution of projects across associates; identify overload

- Consultant Order Backlog: Number of outstanding consultant orders; predict bottlenecks

- Approaching Deadlines: Projects nearing correction response deadlines or other critical milestones

Process Improvement Metrics:

- Process Optimization Impact: Time/cost savings from PI Team initiatives

- New Jurisdiction Ramp-Up Time: Time required to establish procedures and achieve productivity in new market

- Training Effectiveness: Time to productivity for new Design Associates after 1-month training

Quarterly Review Metrics (for Goal Setting Process):

- All Schedule, Quality, Scope, and Resource metrics above

- Compiled by PI Team and provided to Design Management Team

- Used to ensure forecasted goals being met

- Inform continuous improvement, staffing needs, team changes

# Appendix A: Capacity Notes (Non-Canonical)

The following capacity information is provided for context but does not directly impact VS4 workflow or system behavior. These are organizational planning considerations managed outside the value stream scope.

Current Design Team Capacity:

- Current team organization: 2 teams with 4 Design Associates per team = 8 Design Associates

- Design Manager time allocation limits capacity to 4 Design Associates per team (current maximum)

Output of Current Design Team (8 Design Associates):

- High Productivity: 46 weeks per year / 2 weeks per project × 8 Design Associates = 184 projects per year

- • Meets Projected Number of Scheduled Projects for 2025 (140)

- • Meets Projected Number of Scheduled Projects for 2026 (160)

- • Meets Projected Number of Scheduled Projects for 2027 (180)

- Medium Productivity: 46 weeks per year / 2.5 weeks per project × 8 Design Associates = 147 projects per year

- • Meets Projected Number of Scheduled Projects for 2025 (140)

- • Does not meet Projected Number of Scheduled Projects for 2026 (160)

- • Does not meet Projected Number of Scheduled Projects for 2027 (180)

- Low Productivity: 46 weeks per year / 3 weeks per project × 8 Design Associates = 122 projects per year

- • Does not meet Projected Number of Scheduled Projects for 2025 (140)

- • Does not meet Projected Number of Scheduled Projects for 2026 (160)

- • Does not meet Projected Number of Scheduled Projects for 2027 (180)

2026 Staffing Forecast:

- Projected team organization: 3 teams with 3 Design Associates per team = 9 Design Associates

Output of 2026 Design Team (9 Design Associates):

- High Productivity: 46 weeks per year / 2 weeks per project × 9 Design Associates = 207 projects per year

- Medium Productivity: 46 weeks per year / 2.5 weeks per project × 9 Design Associates = 165 projects per year

- Low Productivity: 46 weeks per year / 3 weeks per project × 9 Design Associates = 138 projects per year

- Average Productivity: 170 projects per year

- Meets Projected Number of Scheduled Projects for 2026 (160)

2027 Staffing Forecast:

- Projected team organization: 3 teams with 3-4 Design Associates per team = 10.5 Design Associates

Output of 2027 Design Team (10.5 Design Associates):

- High Productivity: 46 weeks per year / 2 weeks per project × 10.5 Design Associates = 240 projects per year

- Medium Productivity: 46 weeks per year / 2.5 weeks per project × 10.5 Design Associates = 195 projects per year

- Low Productivity: 46 weeks per year / 3 weeks per project × 10.5 Design Associates = 165 projects per year

- Average Productivity: 200 projects per year

- Meets Projected Number of Scheduled Projects for 2027 (180)

Capacity Planning Assumptions:

- Number of work weeks per year per Design Associate is an assumed constant: 52 (weeks in year) - 3 weeks average of holidays - 3 weeks of PTO = 46 weeks

- Productivity Times are variable based on a number of factors including complexity of projects and skill set of Design Associate

- Goals assume intake numbers are not variable - all constraining project information must be received as needed to start the project

- To cover gaps in projected needs, existing roles, skills and potential gaps will be analyzed to make inter-team changes as needed

- Succession has been established within managers to maintain operations when personal or professional extended or short-term leave occurs

- Design Team encourages development of all existing team members to allow roles to be filled internally as they become available

# Appendix B: Insight → Value Stream Mapping

The following table documents how insights from the Design Owner's Manual and other source materials were incorporated into this Value Stream definition:

| Insight Source | What Changed in VS4 | Section Updated | Confidence |
| --- | --- | --- | --- |
| DOM Design: Team Structure | Added specific role definitions; separated Design Manager from Senior Design Manager; removed named individuals | §3 Actors & Roles | High |
| DOM Design: Business Processes | Structured workflow into phases; removed feasibility stages (now VS2 inputs); removed CA stages (now VS6 interface) | §2 Entry/Exit, §4 Workflow | High |
| DOM Design: Detailed Responsibilities | Added comprehensive role responsibilities with specific workflow expectations for each Design Associate level | §3 Actors & Roles, §4 Workflow | High |
| DOM Design: KPIs and Metrics | Imported comprehensive KPI framework; moved capacity math to Appendix A | §10 Metrics, Appendix A | High |
| Existing VS4: SharePoint fragmentation | Preserved pain points about multiple SharePoint sites; no integration with BPO/Connect | §9 Pain Points | High |
| Revision Directive: Scope Cleanup | Removed CA content (now VS6 interface); removed feasibility stages (now VS2 inputs); removed names; moved capacity to appendix | All sections | High |

# Changes Made from v0.7 to v0.8

1. Removed Named Individuals

- All role titles now show counts only (e.g., 'Senior Design Manager (3)' instead of listing names)

- Focus on role definitions and responsibilities rather than specific personnel

2. Removed Construction Administration Content from VS4

- Deleted Phase 6 (all 4 CA stages) from workflow

- Added handoff note to VS6 in Exit Conditions (§2)

- CA Team now referenced as operating within VS6 scope for ongoing construction support

- Removed D8 (Post-Permit Revision Authorization) from decision points

3. Removed Feasibility Stages from VS4

- Deleted Phase 1 (Stages 1.1 and 1.2 feasibility stages) from workflow

- Moved feasibility content to Entry Conditions as 'Inputs from VS2'

- VS4 now begins with Schematic Design phase (previously Phase 2, now Phase 1)

- Removed D1 (Feasibility Design Viability) from decision points

4. Added Additional Detail

- Expanded role responsibilities with specific workflow expectations for each Design Associate level

- Added detailed activities, tools, and constraints to workflow stages

- Included specific software tools (Revit, AutoCAD, Bluebeam, SketchUp, Lumion)

- Added iteration expectations and quality criteria at each stage

- Expanded pain points with specific operational impacts

5. Moved Capacity Information to Appendix

- Created Appendix A: 'Capacity Notes (Non-Canonical)'

- Moved all staffing forecasts (2026: 9 associates, 2027: 10.5 associates)

- Moved productivity calculations and output projections

- Kept only workflow-impacting constraints in §7

6. Updated Decision Points

- Renumbered from D1-D8 to D1-D6 after removing feasibility and CA decisions

- Verified all decision points reference workflow stages within revised VS4 scope

- All decisions now map to Phases 1-4 (Schematic Design through Supporting Deliverables)

7. Structural Improvements

- Clarified Entry/Exit conditions with explicit VS2 and VS6 interfaces

- Distinguished between workflow-impacting constraints (kept in §7) and organizational planning (moved to appendix)

- Enhanced data flows section with clear directional indicators

- Maintained 10-section canonical template structure throughout

## Changes Made from v0.8 to v0.9

1. Implemented Workflow Group & Workflow Numbering System

- Renamed “Phase” → “Workflow Group (WG)”

- Renumbered all stages using VS4-WG#-WF# format with shorthand notation

- Example: “Stage 1.1” → “VS4-WG1-WF1 (4.1.1): Schematic Design Initiation”

- Updated all 4 Workflow Group headers (WG1-WG4)

- Updated all 18 Workflow headers across all Workflow Groups

2. Added Numbering System Reference Section

- New explanatory section in §4 (before WG1)

- Defines three-level hierarchy: Value Stream > Workflow Group > Workflow

- Provides complete WG/WF mapping table:

  - WG1 (4.1): Schematic Design - 3 Workflows

  - WG2 (4.2): Design Development - 6 Workflows

  - WG3 (4.3): Entitlement Execution - 7 Workflows

Blueprint Capital · Value Stream 4: Design & Entitlement · v0.8 · December 2025